## Feasibility Study
BRDB Development Sdn Bhd
Feasibility Study
Lot 1423, Jalan Desa Sentosa KL | [5 empty] | Acre to Sqm | 4046.87
[6 empty] | Acre to Sqft | 43560 | Jalan Desa Sentosa | Phase 1b | Phase 1c | Phase 1d | Phase 1e | Phase 1f |  | Phase 1g | Phase 1h |  |  | Phase 2a | Phase 2B | Phase 2c | Phase 2d | Phase 2e | Phase 2f | Phase 2g1 | Phase 2g2 | Phase 2g3 | Phase 2h
LAUNCH DATE | [7 empty] | TBC | TBC | TBC | TBC | TBC | TBC |  | TBC | TBC |  |  | TBC | TBC | TBC | TBC | TBC | TBC | TBC | TBC | TBC | TBC | TBC | TOTAL
|  | Phases Land Area (acres) => | [5 empty] | 2.938 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.938
|  | Phases Land Area (square meter) => | [5 empty] | 11889.7041 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11889.7041
|  | Phases Land Area (square feet) => | [5 empty] | 127979.28 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 127979.28
|  | No of units in the Phase => | [5 empty] | 84 | #REF! | #REF! | #REF! | 0 | #REF! |  | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0 | #REF! | #REF! | #REF!
|  | Carpark Bays => | [5 empty] | 344 | 0 | 0 | 0 | 0 | 0
|  | Typical Apartment Floor => | [5 empty] | 44
|  | Construction Floor Area include Carpark (CFA) => | [5 empty] | 653039
|  | Gross Floor Area exclude Carpark (GFA) => | [5 empty] | 378439 |  | 1
|  | Net Floor/Saleable area (NFA) => | [5 empty] | 294000 |  | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
|  | Plot Ratio (commercial) / Density (per acres) => | [5 empty] | 2.957 | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #DIV/0! | #REF! | #REF!
|  | Summary |  |  |  |  | %
|  | Net Development Value (NDV) => |  |  |  | 600 | 100% | 176400000
|  | Land Cost => |  |  |  | 100 | 8.495% | -14985575.76
|  | Construction Cost => |  |  |  | 352.4713 | 58.75% | -103626574.35
|  | Soft Cost => |  |  |  | 48.4422 | 8.074% | -14242019.6915
|  | Finance Cost => |  |  |  |  | 3.063% | -5402463.3335
|  | Net Development Profit (NDP) => | [5 empty] | 38143366.865
[7 empty] | Net Profit Margin | 21.62%
A | GROSS DEVELOPMENT VALUE
[13 empty] | Mixed Comm |  | Mixed Comm | Mixed Comm
1 | Type of Development | [6 empty] | Condominium | 3 Sty Superlink | Affordable Home | Affordable Home | Commercial | S. Apartment |  | S.Apartment | S.Apartment |  |  | 2 Sty Linkhouse | 2 Sty Linkhouse | 2 Sty Linkhouse | 2 Sty Semi-D | 2 Sty Semi-D | Zero Lot Bungalow | Condominium | Condominium | Recreational | Terrace House | Commercial Shoplot
2 | Total No of Units | a) Residential | 84 | [8 empty] | Shop-lot | Retail Shoplots |  | Retail Shoplots | Retail Shoplots | [8 empty] | High Rise | High Rise | Park
3 | Net Floor/Saleable Area (NFA) | a) Residential | 294000
4 | Net Selling Price psf | a) Residential | 600 | [5 empty] | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
|  |  | Unit Avg size | Units | RM'psf (Nett to Dev) | Total NFA | Average Price/unit (Nett)
|  | Condominium | [6 empty] | #REF! | [20 empty] | #REF!
|  | Typical Apartment (2 units per floor) | 3500 | 84 | 600 | 294000 | 2100000
GROSS DEVELOPMENT VALUE (GDV) | [7 empty] | 220229268 | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
1 | MARKETING & SELLING EXPENSES | [6 empty] | 43829268 | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
1.1 | Marketing Expenses
| General Marketing Expenses |  |  |  | 1% | of NDV |  | 1764000 | #REF! | 0 | 0 | 0 | 0 |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF!
| Architectural Models | [28 empty] | 0
| Market Research | [28 empty] | 0
| Construction Sales Gallery | [28 empty] | 0
| Yenom Final Acc SG,G/Houseinc landscape |  | 5000000 | [26 empty] | 0
| Construction of Show units (inc. ID) or I.D & Landscape cost for actual unit at site | [28 empty] | 0
Running & maintainance Cost of Sales Gallery & Show unit
1.2 | Selling Expenses
| VIP Discount/Discount/Early Bird |  |  |  | 9% | of GDV |  | 18184068
| Commission & Brokerage |  |  |  | 3% | of NDV |  | 5292000
| Repeat Buyers/BGB |  |  |  | 3% | of NDV |  | 5292000
| Director/Staff Discount |  |  |  | 3% | of NDV |  | 5292000
| Free SPA & Loan Legal Fees |  |  |  | 5000 | /unit |  | 420000
| Bumi Discount |  |  |  | 7% | 50% |  | 6174000
| Maintenance & Sinking Fund |  |  |  | 0.4 | 12 months |  | 1411200
*Net Development Value (NDV) have to be same with S&M based on net selling price after deduction of all discounts (bumi discounts & release penalty), incentives, early birds, Legal Fees & any other items not stated in this Feasibility. Sales have to mark up the selling price accordingly. | [29 empty] | 0
NET DEVELOPMENT VALUE (NDV) | [7 empty] | 176400000 | #REF! | 0 | 0 | 0 | 0 |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF!
[20 empty] | 149873740.8047 |  |  |  |  | 52605702 | 52605702 | 52605702
127869357.8444
Net Selling Price psf | [7 empty] | 600 | #DIV/0! | 0 | #DIV/0! | #DIV/0! | #DIV/0! |  | #DIV/0! | #DIV/0! |  |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
[9 empty] | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
B | GROSS DEVELOPMENT COST (GDC)
[9 empty] | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! |  | #DIV/0! | #DIV/0! |  |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 100
2 | LAND & OTHER RELATED COSTS | [6 empty] | 14985575.76 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14729617.2
[7 empty] | % of NDV | 8.495%
[7 empty] | Land & Other Related Cost psf | 117.0938
| 5.1 | Land Cost |  |  | 100 |  |  | 12797928 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12797928
| 5.2 | Land Conversion Premium | 15% | 30% | 15% or 30% | of Net Land Value |  | 1919689.2 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1919689.2
| 5.3 | Legal Fees |  |  | 2% | of Net Land Value |  | 255958.56
| 5.4 | Quit Rent |  |  | 2000 | per Annum for 4 years |  | 8000 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8000
| 5.5 | Assessment |  |  | 1000 | per Annum for 4 years |  | 4000 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4000
| 5.6 | Valuation Report | [5 empty] | 5000
3 | GROSS CONSTRUCTION COST (GCC) | [6 empty] | 103626574.35 | 0 | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0 | #REF! | #REF! | #REF!
[7 empty] | % of NDV | 58.75% | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #DIV/0! | #REF! | #REF! | #REF!
[7 empty] | Construction Cost psf | 352.4713 | #DIV/0! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
| 3.1 | Building Work
|  | Residential |  |  | 300 |  |  | 88200000 | 0 |  |  |  | #REF! | [5 empty] | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! |  | #REF!
|  | Affordable Housing |  |  | 200 |  |  |  |  | #REF! | #REF! | [18 empty] | #REF!
|  | Commercial Shoplots |  |  | 180 | [6 empty] | #REF! | #REF! |  | #REF! | #REF! | [12 empty] | #REF! | #REF!
Freebies (Optional):
|  | White Goods |  |  |  | /unit
|  | Wardrobe |  |  |  | /unit
| 3.2 | Earthworks to platform level, Retaining structure, External & Internal Infrastructure |  |  | 700000 |  |  | 2056600 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2056600
| 3.3 | Soft Landscape & Hard Landscape |  |  | 125000 |  |  | 367250 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 367250
| 3.4 | Clubhouse / Show Units |  |  | 1000000 |  |  | 1000000 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000000
|  | Construction Cost (CC) | [5 empty] | 91623850 | 0 | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0 | #REF! | #REF! | #REF!
| 3.5 | Preliminary |  |  | 8% | of Construction Cost |  | 7329908 | 0 | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0 | #REF! | #REF! | #REF!
| 3.6 | Contingency |  |  | 5% | of Construction Cost |  | 4581192.5 | 0 | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0 | #REF! | #REF! | #REF!
| 3.7 | SST |  | Commercial Only | 6% | of Construction Cost | [5 empty] | #REF! | #REF! |  | #REF! | #REF! | [12 empty] | #REF! | #REF!
| 3.8 | Contract Stamping Fee |  |  | 0.1% | of Construction Cost |  | 91623.85
4 | STRATA TITLE APPLICATION FEES & SURVEY FEES | [6 empty] | 420000 | #REF! | #REF! | #REF! | 0 | #REF! |  | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0 | #REF! | #REF! | #REF!
[6 empty] | 5000 |  | 420000 | #REF! | #REF! | #REF! | 0 | #REF! |  | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0 | #REF! | #REF! | #REF!
5 | PLANNING SUBMISSION FEES & BUILDING PLAN FEES | [6 empty] | 84000 | #REF! | #REF! | #REF! | 0 | #REF! |  | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0 | #REF! | #REF! | #REF!
[6 empty] | 1000 |  | 84000 | #REF! | #REF! | #REF! | 0 | #REF! |  | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0 | #REF! | #REF! | #REF!
6 | CONTRIBUTION TO AUTHORITIES | [6 empty] | 4301628 | #REF! | #REF! | #REF! | 0 | #REF! |  | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0 | #REF! | #REF! | #REF!
| 9.1 | Development Charges |  |  | 1% | of NDV |  | 1764000 | #REF! | 0 | 0 | 0 | 0 |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF!
| 9.2 | SYABAS |  |  | 0.25% | of NDV |  | 441000 | #REF! | 0 | 0 | 0 | 0 |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF!
| 9.3 | IWK & JPS |  |  | 1% | of NDV |  | 1764000 | #REF! | 0 | 0 | 0 | 0 |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF!
| 9.4 | TNB |  |  | 1750 | per Unit |  | 147000 | #REF! | #REF! | #REF! | 0 | #REF! |  | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0 | #REF! | #REF! | #REF!
| 9.5 | TM Fibre Optic |  |  | 2000 | per Unit |  | 168000 | #REF! | #REF! | #REF! | 0 | #REF! |  | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0 | #REF! | #REF! | #REF!
| 9.6 | Road & Drainage |  |  | 6000 | per Acre |  | 17628 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17628
| 9.7 | School Contribution | [27 empty] | 0
| 9.8 | Improvement Service Fund ("ISF") | [27 empty] | 0
| 9.9 | Green RE
| 9.1 | CONQUAS & QLASSIC
| 9.11 | Hoarding Fee
7 | CONSULTANCY FEES | [6 empty] | 7253860.2045 | 0 | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0 | #REF! | #REF! | #REF!
[5 empty] | 7% | of GCC |  | 7253860.2045 | 0 | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0 | #REF! | #REF! | #REF!
8 | OTHER CONSTRUCTION COST | [6 empty] | 110000 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000
| 8.1 | Soil Investigation | [5 empty] | 100000 | [21 empty] | 100000
| 8.2 | Utility Mapping | [5 empty] | 10000
9 | SITE ADMINISTRATION COST | [6 empty] | 2072531.487 | 0 | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0 | #REF! | #REF! | #REF!
[5 empty] | 2% | of GCC |  | 2072531.487 | 0 | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0 | #REF! | #REF! | #REF!
10 | SHORT TERM OPERATING COST - I.E. SITE SECURITY, SERVICE CHARGES FOR PROVISIONAL BLOCKS | [6 empty] | 0 | [21 empty] | 0
| 10.1 | Site Security |  |  | 0 | per month for 2 years |  | 0
| 10.2 | Service Charges for Provisional Blocks
NET DEVELOPMENT COST (GDC) BEFORE FINANCE CHARGES | [7 empty] | 132854169.8015 | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0 | #REF! | #REF! | #REF!
NET DEVELOPMENT COST (GDC) BEFORE LAND COST | [7 empty] | 120056241.8015 | #REF! | #REF! | #REF! | #REF! | #REF! | 0 | #REF! | #REF! | 0 | 0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0 | #REF! | #REF! | #REF!
NET DEVELOPMENT PROFIT BEFORE FINANCE CHARGES | [7 empty] | 43545830.1985 | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
[8 empty] | 24.69% | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
11 | FINANCE CHARGES | [6 empty] | 5402463.3335 | 0 | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0 | #REF! | #REF! | #REF!
| 11.1 | Land Cost Interest |  | 4.55% | 70% | of Land Cost | 4 | 1630456.0272 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1630456.0272
| 11.2 | Construction Loan Interest |  | 4.55% | 20% | of GCC | 4 | 3772007.3063 | 0 | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0 | #REF! | #REF! | #REF!
NET DEVELOPMENT COST (GDC) AFTER FINANCIAL CHARGES | [7 empty] | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
NET DEVELOPMENT PROFIT (NDP) AFTER FINANCIAL CHARGES | [7 empty] | 38143366.865 | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
[8 empty] | 21.62% | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
12 | PROJECT DEPARTMENT OVERHEAD |  |  |  | 1.4% | of NDV |  |  | #REF! | 0 | 0 | 0 | 0 |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF!
13 | HEAD OFFICE OVERHEAD |  |  |  | 3% | of NDV |  |  | #REF! | 0 | 0 | 0 | 0 |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF!
14 | MARKETING DEPARTMENT OVERHEAD |  |  |  | 0.5% | of NDV |  |  | #REF! | 0 | 0 | 0 | 0 |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF!
15 | CORPORATE OVERHEAD |  |  |  | 1% | of NDV |  |  | #REF! | 0 | 0 | 0 | 0 |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF!
[8 empty] | 0 | #REF! | 0 | 0 | 0 | 0 |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF!
NET DEVELOPMENT PROFIT (NDP) AFTER HEAD OFFICE OVERHEAD | [7 empty] | 38143366.865 | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
% (NDP/NDV) | [7 empty] | 21.62% | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Note on U3: 28185m2 - 12140.61m2 = 16044.39m2
Note on Y17: Jeremy Tan Jin Bang: KM Condition: - 4.40ac for Comm Plot - 0.94ac for R.Pond Only maximize comm plot.
Note on AW17: Jeremy Tan Jin Bang: KM Condition: - 4.40ac for Comm Plot - 0.94ac for R.Pond Only maximize comm plot.
Note on BA41: Jeremy Tan Jin Bang: 2% NDV
Note on AE58: Hana Nordin: 3.25%
Note on AE62: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: GDV for all units 173
Note on AE63: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: NDV for all units 173
Note on U72: Khairul Nadzrin Bin Hashim: will be based on RM50 psf
Note on M79: 35,815,413 - P1 common infra - common landscape = 33,516,525 ie Prinsiptek contract
Note on BA93: Jeremy Tan Jin Bang: Follow QS estimate RM1.69 psf to GFA 1477653sqft
Note on I96: 64.6+114.67=179.27ac + 20.3ac land for sale = 199.57ac
Note on K96: 64.6+114.67=179.27ac + 20.3ac land for sale = 199.57ac
Note on M96: 64.6+114.67=179.27ac + 20.3ac land for sale = 199.57ac
Note on O96: 64.6+114.67=179.27ac + 20.3ac land for sale = 199.57ac
Note on Q96: 64.6+114.67=179.27ac + 20.3ac land for sale = 199.57ac
Note on S96: 64.6+114.67=179.27ac + 20.3ac land for sale = 199.57ac
Note on U96: 64.6+114.67=179.27ac + 20.3ac land for sale = 199.57ac
Note on W96: 64.6+114.67=179.27ac + 20.3ac land for sale = 199.57ac
Note on Y96: 64.6+114.67=179.27ac + 20.3ac land for sale = 199.57ac
Note on AC96: 64.6+114.67=179.27ac + 20.3ac land for sale = 199.57ac
Note on AE96: 64.6+114.67=179.27ac + 20.3ac land for sale = 199.57ac
Note on AG96: 64.6+114.67=179.27ac + 20.3ac land for sale = 199.57ac
Note on AI96: 64.6+114.67=179.27ac + 20.3ac land for sale = 199.57ac
Note on AK96: 64.6+114.67=179.27ac + 20.3ac land for sale = 199.57ac
Note on AM96: 64.6+114.67=179.27ac + 20.3ac land for sale = 199.57ac
Note on AO96: 64.6+114.67=179.27ac + 20.3ac land for sale = 199.57ac
Note on AQ96: 64.6+114.67=179.27ac + 20.3ac land for sale = 199.57ac
Note on AS96: 64.6+114.67=179.27ac + 20.3ac land for sale = 199.57ac
Note on AU96: 64.6+114.67=179.27ac + 20.3ac land for sale = 199.57ac
Note on AW96: 64.6+114.67=179.27ac + 20.3ac land for sale = 199.57ac
Note on BA96: 64.6+114.67=179.27ac + 20.3ac land for sale = 199.57ac
Note on BA99: Jeremy Tan Jin Bang: 2% instead of 3%
Note on Q100: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Assume commercial area is 10% of total GFA
Note on S100: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Assume commercial area is 10% of total GFA
Note on W100: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Assume commercial area is 10% of total GFA
Note on Y100: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Assume commercial area is 10% of total GFA
Note on AW100: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Assume commercial area is 10% of total GFA
Note on AZ109: Hana Nordin: savings
Note on BA112: Jeremy Tan Jin Bang: 1% of GDV
Note on I126: 64.6+114.67-3=176.27ac
Note on K126: 64.6+114.67-3=176.27ac
Note on M126: 64.6+114.67-3=176.27ac
Note on O126: 64.6+114.67-3=176.27ac
Note on Q126: 64.6+114.67-3=176.27ac
Note on S126: 64.6+114.67-3=176.27ac
Note on U126: 64.6+114.67-3=176.27ac
Note on W126: 64.6+114.67-3=176.27ac
Note on Y126: 64.6+114.67-3=176.27ac
Note on AC126: 64.6+114.67-3=176.27ac
Note on AE126: 64.6+114.67-3=176.27ac
Note on AG126: 64.6+114.67-3=176.27ac
Note on AI126: 64.6+114.67-3=176.27ac
Note on AK126: 64.6+114.67-3=176.27ac
Note on AM126: 64.6+114.67-3=176.27ac
Note on AO126: 64.6+114.67-3=176.27ac
Note on AQ126: 64.6+114.67-3=176.27ac
Note on AS126: 64.6+114.67-3=176.27ac
Note on AU126: 64.6+114.67-3=176.27ac
Note on AW126: 64.6+114.67-3=176.27ac
Note on BA126: 64.6+114.67-3=176.27ac
Note on BA129: Jeremy Tan Jin Bang: 2% of GCC
Note on AZ137: Hana Nordin: savings

## Cashflow
BRDB LAND — MONTHLY CASHFLOW MODEL (RM'000)
All values RM'000 ¦ Blue = inputs ¦ Black = formulas ¦ Green = linked from Feasibility Study
|  | Year 1 | [11 empty] | Year 2 | [11 empty] | Year 3 | [11 empty] | Year 4 | [11 empty] | Year 5
DESCRIPTION | BASIS / TOTAL (RM'000) | Jan '26 | Feb '26 | Mar '26 | Apr '26 | May '26 | Jun '26 | Jul '26 | Aug '26 | Sep '26 | Oct '26 | Nov '26 | Dec '26 | Jan '27 | Feb '27 | Mar '27 | Apr '27 | May '27 | Jun '27 | Jul '27 | Aug '27 | Sep '27 | Oct '27 | Nov '27 | Dec '27 | Jan '28 | Feb '28 | Mar '28 | Apr '28 | May '28 | Jun '28 | Jul '28 | Aug '28 | Sep '28 | Oct '28 | Nov '28 | Dec '28 | Jan '29 | Feb '29 | Mar '29 | Apr '29 | May '29 | Jun '29 | Jul '29 | Aug '29 | Sep '29 | Oct '29 | Nov '29 | Dec '29 | Jan '30 | Feb '30 | Mar '30 | Apr '30 | May '30 | Jun '30 | Jul '30 | Aug '30 | Sep '30 | Oct '30 | Nov '30 | Dec '30 | TOTAL
Start date | time axis 2026-01-01 to 2030-12-01
A. PROJECT ASSUMPTIONS
Project name | BRDB Land Development
Development period (years) | 5
Project start | January 2026
Total GDV (RM'000) | #REF!
Total NDV (RM'000) | #REF!
Total GDC (RM'000) | #REF!
Total NDP (RM'000) | #REF!
Land cost (RM'000) | 12797.928
Construction cost (RM'000) | #REF!
Annual interest rate | 4.55%
Target IRR (hurdle) | 16%
B. MONTHLY SALES ABSORPTION SCHEDULE (% of NDV collected per month)
S-curve absorption — slow launch M1–M6, peak Y2–Y3, tail-off Y4–Y5. Edit % in blue.
Phase | Type | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Total %
Ph 1a | residential | 1% | 1% | 1% | 2% | 2% | 2% | 2% | 2% | 2% | 3% | 3% | 3% | 3% | 3% | 3% | 4% | 4% | 4% | 4% | 4% | 4% | 4% | 3% | 3% | 3% | 3% | 3% | 2% | 2% | 2% | 2% | 2% | 2% | 2% | 2% | 2% | 1% | 1% | 1% | 1% | 1% | 1% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100%
Ph 1b | residential | 1% | 1% | 1% | 2% | 2% | 2% | 2% | 2% | 2% | 3% | 3% | 3% | 3% | 3% | 3% | 4% | 4% | 4% | 4% | 4% | 4% | 4% | 3% | 3% | 3% | 3% | 3% | 2% | 2% | 2% | 2% | 2% | 2% | 2% | 2% | 2% | 1% | 1% | 1% | 1% | 1% | 1% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100%
Ph 1c | affordable | 2% | 2% | 3% | 3% | 3% | 5% | 4% | 4% | 4% | 4% | 4% | 4% | 4% | 4% | 4% | 4% | 3% | 3% | 3% | 3% | 3% | 3% | 3% | 3% | 2% | 2% | 2% | 2% | 2% | 2% | 1% | 1% | 1% | 1% | 1% | 1% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100%
Ph 1d | affordable | 2% | 2% | 3% | 3% | 3% | 5% | 4% | 4% | 4% | 4% | 4% | 4% | 4% | 4% | 4% | 4% | 3% | 3% | 3% | 3% | 3% | 3% | 3% | 3% | 2% | 2% | 2% | 2% | 2% | 2% | 1% | 1% | 1% | 1% | 1% | 1% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100%
Ph 1e | commercial | 2% | 3% | 3% | 4% | 4% | 4% | 4% | 4% | 5% | 5% | 5% | 5% | 5% | 5% | 5% | 5% | 4% | 4% | 4% | 4% | 3% | 3% | 2% | 2% | 1% | 1% | 1% | 1% | 1% | 1% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100%
Ph 1f | residential | 1% | 1% | 1% | 2% | 2% | 2% | 2% | 2% | 2% | 3% | 3% | 3% | 3% | 3% | 3% | 4% | 4% | 4% | 4% | 4% | 4% | 4% | 3% | 3% | 3% | 3% | 3% | 2% | 2% | 2% | 2% | 2% | 2% | 2% | 2% | 2% | 1% | 1% | 1% | 1% | 1% | 1% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100%
Ph 1g | commercial | 2% | 3% | 3% | 4% | 4% | 4% | 4% | 4% | 5% | 5% | 5% | 5% | 5% | 5% | 5% | 5% | 4% | 4% | 4% | 4% | 3% | 3% | 2% | 2% | 1% | 1% | 1% | 1% | 1% | 1% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100%
Ph 1h | commercial | 2% | 3% | 3% | 4% | 4% | 4% | 4% | 4% | 5% | 5% | 5% | 5% | 5% | 5% | 5% | 5% | 4% | 4% | 4% | 4% | 3% | 3% | 2% | 2% | 1% | 1% | 1% | 1% | 1% | 1% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100%
Ph 2a | residential | 1% | 1% | 1% | 2% | 2% | 2% | 2% | 2% | 2% | 3% | 3% | 3% | 3% | 3% | 3% | 4% | 4% | 4% | 4% | 4% | 4% | 4% | 3% | 3% | 3% | 3% | 3% | 2% | 2% | 2% | 2% | 2% | 2% | 2% | 2% | 2% | 1% | 1% | 1% | 1% | 1% | 1% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100%
Ph 2b | residential | 1% | 1% | 1% | 2% | 2% | 2% | 2% | 2% | 2% | 3% | 3% | 3% | 3% | 3% | 3% | 4% | 4% | 4% | 4% | 4% | 4% | 4% | 3% | 3% | 3% | 3% | 3% | 2% | 2% | 2% | 2% | 2% | 2% | 2% | 2% | 2% | 1% | 1% | 1% | 1% | 1% | 1% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100%
Ph 2c | residential | 1% | 1% | 1% | 2% | 2% | 2% | 2% | 2% | 2% | 3% | 3% | 3% | 3% | 3% | 3% | 4% | 4% | 4% | 4% | 4% | 4% | 4% | 3% | 3% | 3% | 3% | 3% | 2% | 2% | 2% | 2% | 2% | 2% | 2% | 2% | 2% | 1% | 1% | 1% | 1% | 1% | 1% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100%
Ph 2d | residential | 1% | 1% | 1% | 2% | 2% | 2% | 2% | 2% | 2% | 3% | 3% | 3% | 3% | 3% | 3% | 4% | 4% | 4% | 4% | 4% | 4% | 4% | 3% | 3% | 3% | 3% | 3% | 2% | 2% | 2% | 2% | 2% | 2% | 2% | 2% | 2% | 1% | 1% | 1% | 1% | 1% | 1% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100%
Ph 2e | residential | 1% | 1% | 1% | 2% | 2% | 2% | 2% | 2% | 2% | 3% | 3% | 3% | 3% | 3% | 3% | 4% | 4% | 4% | 4% | 4% | 4% | 4% | 3% | 3% | 3% | 3% | 3% | 2% | 2% | 2% | 2% | 2% | 2% | 2% | 2% | 2% | 1% | 1% | 1% | 1% | 1% | 1% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100%
Ph 2f | residential | 1% | 1% | 1% | 2% | 2% | 2% | 2% | 2% | 2% | 3% | 3% | 3% | 3% | 3% | 3% | 4% | 4% | 4% | 4% | 4% | 4% | 4% | 3% | 3% | 3% | 3% | 3% | 2% | 2% | 2% | 2% | 2% | 2% | 2% | 2% | 2% | 1% | 1% | 1% | 1% | 1% | 1% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100%
Ph 2g1 | residential | 1% | 1% | 1% | 2% | 2% | 2% | 2% | 2% | 2% | 3% | 3% | 3% | 3% | 3% | 3% | 4% | 4% | 4% | 4% | 4% | 4% | 4% | 3% | 3% | 3% | 3% | 3% | 2% | 2% | 2% | 2% | 2% | 2% | 2% | 2% | 2% | 1% | 1% | 1% | 1% | 1% | 1% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100%
Ph 2g2 | residential | 1% | 1% | 1% | 2% | 2% | 2% | 2% | 2% | 2% | 3% | 3% | 3% | 3% | 3% | 3% | 4% | 4% | 4% | 4% | 4% | 4% | 4% | 3% | 3% | 3% | 3% | 3% | 2% | 2% | 2% | 2% | 2% | 2% | 2% | 2% | 2% | 1% | 1% | 1% | 1% | 1% | 1% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100%
Ph 2h | residential | 1% | 1% | 1% | 2% | 2% | 2% | 2% | 2% | 2% | 3% | 3% | 3% | 3% | 3% | 3% | 4% | 4% | 4% | 4% | 4% | 4% | 4% | 3% | 3% | 3% | 3% | 3% | 2% | 2% | 2% | 2% | 2% | 2% | 2% | 2% | 2% | 1% | 1% | 1% | 1% | 1% | 1% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100%
Ph 2j | commercial | 2% | 3% | 3% | 4% | 4% | 4% | 4% | 4% | 5% | 5% | 5% | 5% | 5% | 5% | 5% | 5% | 4% | 4% | 4% | 4% | 3% | 3% | 2% | 2% | 1% | 1% | 1% | 1% | 1% | 1% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100%
C. SALES RECEIPTS (RM'000) — NDV × Monthly Absorption %
Phase | NDV (RM'000) | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Total
Ph 1a | 176400 | 1764 | 1764 | 1764 | 3528 | 3528 | 3528 | 3528 | 3528 | 3528 | 5292 | 5292 | 5292 | 5292 | 5292 | 5292 | 7056 | 7056 | 7056 | 7056 | 7056 | 7056 | 7056 | 5292 | 5292 | 5292 | 5292 | 5292 | 3528 | 3528 | 3528 | 3528 | 3528 | 3528 | 3528 | 3528 | 3528 | 1764 | 1764 | 1764 | 1764 | 1764 | 1764 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 176400
Ph 1b | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Ph 1c | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Ph 1d | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Ph 1e | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Ph 1f | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Ph 1g | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Ph 1h | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Ph 2a | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Ph 2b | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Ph 2c | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Ph 2d | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Ph 2e | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Ph 2f | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Ph 2g1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Ph 2g2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Ph 2h | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Ph 2j | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TOTAL SALES RECEIPTS |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
D. LAND COST (RM'000) — Deposit M1, Balance spread M2–M12
Item | Total | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Total
Deposit (10%) | 1279.7928 | 1279.7928 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | 1279.7928
Balance SPA — M2–M6 | 5759.0676 | - | 1151.8135 | 1151.8135 | 1151.8135 | 1151.8135 | 1151.8135 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | 5759.0676
Balance SPA — M7–M12 | 5759.0676 | - | - | - | - | - | - | 959.8446 | 959.8446 | 959.8446 | 959.8446 | 959.8446 | 959.8446 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | 5759.0676
Land conversion premium | 1919.6892 | - | - | - | - | - | - | - | - | - | - | - | 1919.6892 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | 1919.6892
TOTAL LAND COST |  | 1279.7928 | 1151.8135 | 1151.8135 | 1151.8135 | 1151.8135 | 1151.8135 | 959.8446 | 959.8446 | 959.8446 | 959.8446 | 959.8446 | 2879.5338 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14717.6172
E. CONSTRUCTION COST (RM'000) — S-curve drawdown over 48 months
Item | Total (RM'000) | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Total
Building works — residential (55%) | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | - | - | - | - | - | - | - | - | - | - | - | - | - | #REF!
Building works — commercial (15%) | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | - | - | - | - | - | - | - | - | - | - | - | - | - | #REF!
Earthworks & infrastructure (15%) | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | - | - | - | - | - | - | - | - | - | - | - | - | - | #REF!
Prelims & contingency (13%) | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | - | - | - | - | - | - | - | - | - | - | - | - | - | #REF!
Consultancy fees (6.5% of GCC) | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | - | - | - | - | - | - | - | - | - | - | - | - | - | #REF!
TOTAL CONSTRUCTION COST |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
F. OVERHEADS & MARKETING (RM'000) — spread evenly over 60 months
Item | Total (RM'000) | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Total
Marketing & selling expenses (4% NDV) | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Project dept overhead (1.4% NDV) | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Head office overhead (3% NDV) | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Corporate overhead (1% NDV) | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Site admin cost (2% GCC) | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Statutory contributions (3% NDV) | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
TOTAL OVERHEADS & MARKETING |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
TOTAL OUTFLOWS |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
G. NET CASHFLOW SUMMARY
Item |  | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Total
Total inflows (sales receipts) |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Total outflows |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
NET CASHFLOW |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
CUMULATIVE CASHFLOW |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
PEAK EQUITY EXPOSURE (minimum cumulative cashflow) |  | Total: #REF!

## Returns
BRDB LAND — RETURNS & SENSITIVITY ANALYSIS
All values RM'000 ¦ XIRR on 60 monthly cashflows ¦ Blue = inputs ¦ Green = linked from other sheets
A. PROJECT SUMMARY
Total GDV (RM'000) | #REF!
Total NDV (RM'000) | #REF!
Gross dev cost — GDC (RM'000) | #REF!
Net dev profit — NDP (RM'000) | #REF!
Dev margin % on NDV | #REF!
Land cost (RM'000) | 12797.928
Construction cost (RM'000) | #REF!
Peak equity exposure (RM'000) | #REF!
Development period (years) | BRDB Land Development
B. EQUITY CASHFLOW SCHEDULE — Input for XIRR
Equity invested = outflows up to peak; equity repaid = inflows after peak. Dates set to quarterly from project start.
Quarter | Date | Net CF (RM'000) | Cumulative (RM'000)
Y1 M01 | 2026-01-01 | #REF! | #REF!
Y1 M02 | 2026-02-01 | #REF! | #REF!
Y1 M03 | 2026-03-01 | #REF! | #REF!
Y1 M04 | 2026-04-01 | #REF! | #REF!
Y1 M05 | 2026-05-01 | #REF! | #REF!
Y1 M06 | 2026-06-01 | #REF! | #REF!
Y1 M07 | 2026-07-01 | #REF! | #REF!
Y1 M08 | 2026-08-01 | #REF! | #REF!
Y1 M09 | 2026-09-01 | #REF! | #REF!
Y1 M10 | 2026-10-01 | #REF! | #REF!
Y1 M11 | 2026-11-01 | #REF! | #REF!
Y1 M12 | 2026-12-01 | #REF! | #REF!
Y2 M01 | 2027-01-01 | #REF! | #REF!
Y2 M02 | 2027-02-01 | #REF! | #REF!
Y2 M03 | 2027-03-01 | #REF! | #REF!
Y2 M04 | 2027-04-01 | #REF! | #REF!
Y2 M05 | 2027-05-01 | #REF! | #REF!
Y2 M06 | 2027-06-01 | #REF! | #REF!
Y2 M07 | 2027-07-01 | #REF! | #REF!
Y2 M08 | 2027-08-01 | #REF! | #REF!
Y2 M09 | 2027-09-01 | #REF! | #REF!
Y2 M10
Y2 M11 | 2027-11-01 | #REF! | #REF!
Y2 M12 | 2027-12-01 | #REF! | #REF!
Y3 M01 | 2028-01-01 | #REF! | #REF!
Y3 M02 | 2028-02-01 | #REF! | #REF!
Y3 M03 | 2028-03-01 | #REF! | #REF!
Y3 M04 | 2028-04-01 | #REF! | #REF!
Y3 M05 | 2028-05-01 | #REF! | #REF!
Y3 M06 | 2028-06-01 | #REF! | #REF!
Y3 M07 | 2028-07-01 | #REF! | #REF!
Y3 M08 | 2028-08-01 | #REF! | #REF!
Y3 M09 | 2028-09-01 | #REF! | #REF!
Y3 M10 | 2028-10-01 | #REF! | #REF!
Y3 M11
Y3 M12
Y4 M01 | 2029-01-01 | #REF! | #REF!
Y4 M02 | 2029-02-01 | #REF! | #REF!
Y4 M03 | 2029-03-01 | #REF! | #REF!
Y4 M04 | 2029-04-01 | #REF! | #REF!
Y4 M05 | 2029-05-01 | #REF! | #REF!
Y4 M06 | 2029-06-01 | #REF! | #REF!
Y4 M07 | 2029-07-01 | #REF! | #REF!
Y4 M08 | 2029-08-01 | #REF! | #REF!
Y4 M09
Y4 M10
Y4 M11 | 2029-11-01 | #REF! | #REF!
Y4 M12 | 2029-12-01 | #REF! | #REF!
Y5 M01 | 2030-01-01 | #REF! | #REF!
Y5 M02 | 2030-02-01 | #REF! | #REF!
Y5 M03 | 2030-03-01 | #REF! | #REF!
Y5 M04 | 2030-04-01 | #REF! | #REF!
Y5 M05 | 2030-05-01 | #REF! | #REF!
Y5 M06 | 2030-06-01 | #REF! | #REF!
Y5 M07
Y5 M08
Y5 M09 | 2030-09-01 | #REF! | #REF!
Y5 M10 | 2030-10-01 | #REF! | #REF!
Y5 M11 | 2030-11-01 | #REF! | #REF!
Y5 M12 | 2030-12-01 | #REF! | #REF!
C. RETURN METRICS — Based on 60 monthly cashflows (XIRR & NPV)
XIRR annualises internal rate of return on exact dated cashflows. NPV uses monthly discount rate. MOIC = total cash return ÷ peak equity invested.
Project IRR (XIRR — 60 monthly CFs) | Inputs needed
Equity IRR (XIRR on equity cashflows) | Inputs needed
NPV @ 12% hurdle (RM'000) | N/A
NPV @ 15% hurdle (RM'000) | N/A
NPV @ 18% hurdle (RM'000) | N/A
Total return NDV − GDC (RM'000) | Inputs needed
Equity multiple MOIC | N/A
Dev margin % on NDV | N/A
Dev margin % on GDV | N/A
Payback period (months to positive cumulative CF) | Not within 5 years
D. IRR SENSITIVITY — ASP psf vs Absorption Rate (Excel Data Table)
Yellow = base case (RM680 psf / 80% absorption). Green ≥ 16% hurdle ¦ Amber 12–15.9% ¦ Red < 12%. This is a live Excel Data Table — changing Cashflow inputs auto-updates all cells.
|  |  | 680 | 80%
|  |  | Abs → / ASP ↓ | 60% | 70% | ★ 80% | 90% | 100%
|  |  | RM 544 (−20%) | N/A | N/A | N/A | N/A | N/A
|  |  | RM 612 (−10%) | N/A | N/A | N/A | N/A | N/A
|  |  | RM 680 (Base) | N/A | N/A | N/A | N/A | N/A
|  |  | RM 748 (+10%) | N/A | N/A | N/A | N/A | N/A
|  |  | RM 816 (+20%) | N/A | N/A | N/A | N/A | N/A
|  |  | Colour guide: | ≥ 16% — above hurdle | 12–15.9% — below hurdle | < 12% — significantly below
E. NDP MARGIN SENSITIVITY — ASP psf vs Absorption Rate
NDP margin = (NDV_adj − GDC) ÷ NDV_adj. NDV adjusted by ASP and absorption factors relative to base case. GDC held constant.
|  |  | 680 | 0% | 0% | 0% | 0% | 0%
|  |  | Abs → / ASP ↓ | 0% | 0% | 0% | 0% | 0%
|  |  | RM 544 (−20%) | 0% | 0% | 0% | 0% | 0%
|  |  | RM 612 (−10%) | 0% | 0% | 0% | 0% | 0%
|  |  | RM 680 (Base) | 0% | 0% | 0% | 0% | 0%
|  |  | RM 748 (+10%) | 0% | 0% | 0% | 0% | 0%
|  |  | RM 816 (+20%) | 0% | 0% | 0% | 0% | 0%
|  |  | Colour guide: | ≥ 25% margin | 15–24.9% | < 15%
F. NPV SENSITIVITY — Discount Rate vs Absorption Rate (RM'000)
Monthly NPV scaled by absorption factor. Shows how NPV changes as both required return and sales velocity vary.
|  |  | Abs → Discount ↓ | 60% | 70% | ★ 80% | 90% | 100%
|  |  | 10% | N/A | N/A | N/A | N/A | N/A
|  |  | 12% | N/A | N/A | N/A | N/A | N/A
|  |  | 15% (hurdle) | N/A | N/A | N/A | N/A | N/A
|  |  | 18% | N/A | N/A | N/A | N/A | N/A
|  |  | 20% | N/A | N/A | N/A | N/A | N/A
G. LAND COST BREAKEVEN — Max land cost to achieve target IRR (RM'000)
Max land = NDV_adj × (1 − target margin) − GDC_ex_land. GDC_ex_land = GDC − current land cost. Target margin = 25%. Use these figures in SPA price negotiation.
|  |  | ASP psf | Base NDV | NDV_adj | GDC ex-land | Max land (25% margin) | Max land psf | vs current | Deal indicator
|  |  | RM 544 | #REF! | #REF! | #REF! | #REF! | 0 | 0% | #REF!
| 0% | Inputs needed | 0% | #REF! | #REF! | #REF! | #REF! | 0 | 0% | #REF!
|  |  | RM 680 | #REF! | #REF! | #REF! | #REF! | 0 | 0% | #REF!
|  |  | RM 748 | #REF! | #REF! | #REF! | #REF! | 0 | 0% | #REF!
|  |  | RM 816 | #REF! | #REF! | #REF! | #REF! | 0 | 0% | #REF!
H. SCENARIO COMPARISON — Bear / Base / Bull
Bear: ASP −20%, absorption 60%, 1yr delay. Base: as modelled. Bull: ASP +15%, absorption 100%, faster launch.
|  |  | Metric | Bear 🐻 | Base ★ | Bull 🐂
|  |  | ASP psf | RM 544 | RM 680 | RM 782
|  |  | Absorption rate | 60% | 80% | 100%
|  |  | NDV adj (RM'000) | #REF! | #REF! | #REF!
|  |  | GDC (RM'000) | #REF! | #REF! | #REF!
|  |  | NDP (RM'000) | #REF! | #REF! | #REF!
|  |  | NDP margin | 0% | 0% | 0%
|  |  | Approx. IRR | 0% | Inputs needed | 0%
|  |  | MOIC | 0 | 0 | 0
I. CONSTRUCTION COST SENSITIVITY — Build Cost psf vs ASP psf (NDP Margin %)
Shows NDP margin as construction cost varies ±20%. Useful for stress-testing build cost inflation against selling price assumptions.
|  |  | ASP → Build cost ↓ | RM 544 (-2%) | RM 612 (-1%) | RM 680 (★ Base) | RM 748 (+1%) | RM 816 (+2%)
|  |  | RM 224 (−20%) | 0% | 0% | 0% | 0% | 0%
|  |  | RM 252 (−10%) | 0% | 0% | 0% | 0% | 0%
|  |  | RM 280 (Base) | 0% | 0% | 0% | 0% | 0%
|  |  | RM 308 (+10%) | 0% | 0% | 0% | 0% | 0%
|  |  | RM 336 (+20%) | 0% | 0% | 0% | 0% | 0%
NOTES: (1) XIRR formula requires non-zero cashflows — populate unit counts and pricing in Feasibility Study tab first. (2) Sensitivity matrices use linear factor scaling of base XIRR — indicative only; actual IRR will differ due to non-linear CF timing. (3) Land cost breakeven assumes 25% target NDP margin on adjusted NDV. (4) NPV uses monthly discount rate (annual ÷ 12).

## IRR & Sensitivity
BRDB LAND — IRR, NPV & SENSITIVITY ANALYSIS
XIRR on 60 monthly cashflows ¦ NPV @ 3 hurdle rates ¦ Colour-coded sensitivity matrices ¦ Land cost breakeven ¦ Blue = inputs changeable by user
A. ASSUMPTIONS & INPUTS |  | C. SENSITIVITY — PROJECT IRR (%) vs ASP × ABSORPTION | [7 empty] | E. SENSITIVITY — IRR (%) vs CONSTRUCTION COST × ASP
Base ASP (RM psf) | 680 | IRR scales with ASP (revenue) and absorption rate. Yellow = base case. Green ≥ hurdle. Red < hurdle. | [7 empty] | Construction cost deviation vs ASP deviation. Base: RM 280 psf build cost, RM 680 psf ASP.
Base absorption rate | 80% | Absorption ↓ ASP → | RM 476 −30% | RM 544 −20% | RM 612 −10% | RM 680 Base | RM 748 +10% | RM 816 +20% | RM 884 +30% | Constr cost ↓ ASP → | RM 476 −30% | RM 544 −20% | RM 612 −10% | RM 680 Base | RM 748 +10% | RM 816 +20% | RM 884 +30%
Base build cost (RM psf) | 280 | 50% absorption | 0% | 0% | 0% | 0% | 0% | 0% | 0% | CC −30% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
Target hurdle IRR | 16% | 65% absorption | 0% | 0% | 0% | 0% | 0% | 0% | 0% | CC −20% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
Annual interest rate | 4.55% | 80% absorption | 0% | 0% | 0% | 0% | 0% | 0% | 0% | CC −10% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | 95% absorption | 0% | 0% | 0% | 0% | 0% | 0% | 0% | CC Base | 0% | 0% | 0% | 0% | 0% | 0% | 0%
Total GDV (RM'000) | #REF! | 110% absorption | 0% | 0% | 0% | 0% | 0% | 0% | 0% | CC +10% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
Total NDV (RM'000) | #REF! | [8 empty] | CC +20% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
Total GDC (RM'000) | #REF! | D. SENSITIVITY — NDP MARGIN (%) vs ASP × ABSORPTION | [7 empty] | CC +30% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
Total NDP (RM'000) | #REF! | NDP margin = (NDV×ASP×Abs − GDC) / (NDV×ASP×Abs). Green ≥ 25% ¦ Amber 15–25% ¦ Red < 15%
Land cost (RM'000) | 12797.928 | Absorption ↓ ASP → | RM 476 −30% | RM 544 −20% | RM 612 −10% | RM 680 Base | RM 748 +10% | RM 816 +20% | RM 884 +30% | F. MAX LAND COST BREAKEVEN vs ASP (RM'000)
Construction cost (RM'000) | #REF! | 50% absorption | 0% | 0% | 0% | 0% | 0% | 0% | 0% | Max land cost payable to still achieve target IRR (16%). Useful for land price negotiation.
Peak equity exposure (RM'000) | #REF! | 65% absorption | 0% | 0% | 0% | 0% | 0% | 0% | 0% | ASP (RM psf) | NDV adj (RM'000) | GDC ex-land | Target return | Max land cost (RM'000) | Max land psf (RM) | vs current land cost | Viable?
|  | 80% absorption | 0% | 0% | 0% | 0% | 0% | 0% | 0% | RM 476 | #REF! | #REF! | #REF! | #REF! | 0 | 0% | #REF!
Dev margin % on NDV | 0% | 95% absorption | 0% | 0% | 0% | 0% | 0% | 0% | 0% | RM 544 | #REF! | #REF! | #REF! | #REF! | 0 | 0% | #REF!
Dev margin % on GDV | 0% | 110% absorption | 0% | 0% | 0% | 0% | 0% | 0% | 0% | RM 612 | #REF! | #REF! | #REF! | #REF! | 0 | 0% | #REF!
MOIC (NDP / peak equity) | 0 | [8 empty] | RM 680 | #REF! | #REF! | #REF! | #REF! | 0 | 0% | #REF!
[10 empty] | RM 748 | #REF! | #REF! | #REF! | #REF! | 0 | 0% | #REF!
KEY & NOTES | [9 empty] | RM 816 | #REF! | #REF! | #REF! | #REF! | 0 | 0% | #REF!
Green cells | IRR ≥ hurdle (Cashflow!B18) or NDP margin ≥ 25% | [8 empty] | RM 884 | #REF! | #REF! | #REF! | #REF! | 0 | 0% | #REF!
Red cells | IRR < hurdle or NDP margin < 15%
Amber cells | NDP margin between 15–25%
Yellow cell | Base case (RM 680 psf ASP, 80% absorption)
XIRR formula | Monthly cash flows; dates auto-linked from Returns sheet rows 19–78
IRR scaling | Proportional to revenue (ASP × Abs); accurate within ±15% of base case
Land breakeven | Target dev margin = 25% of NDV; edit formula directly to change target
Update model | Fill unit counts & prices in Feasibility Study — all cells auto-update
Total NDP — absolute return (RM'000) | Inputs needed